Project Plan

Gym Buddies - Workout Buddy Finder

| Industry Partner |  |
| --- | --- |
| Primary Instructor | Anjana Shag |
| Team Member | Jacob Solano |
| Team Member | Nhu Nam Nguyen |
| Team Member | Ronan Behan |
| Team Member | Duc Thien Tran |
| Team Member | Simon Vu |

Document Revision History

| Revision # | Date |
| --- | --- |
| 1.0 | October 7, 2024 |

Table of Contents

1.     Executive Summary – 4

2.     Project Approvers, Reviews and Distribution List – 4-5

3.     Scope – 5-6

4.     Deliverables – 6

5.     Assumptions – 6-7

6.     Dependencies – 7

7.     Risk Management – 7-8

8.     Communication – 8

a.     Reporting – 8

b.     Meetings – 8

9.     Task Listing (WBS – Work Breakdown Structure – 9-12

10.  Budget – 12-13

11.  Milestones – 13

12.  Approval – 14

1. Executive Summary

| Objective | Develop a mobile application called GymBuddies that connects users with compatible workout partners based on fitness goals, schedules, and location preferences. |
| --- | --- |
| Corporate Goals Addressed | Create innovative software solutions for real-world problems Enhance user engagement in fitness activities Foster a community of mutual support and motivation in health and wellness |
| Planned Start Date | September 16, 2024 |
| Planned End Date | March 28, 2025 |

2. Project Approvers, Reviews and Distribution List

Approvers, reviewers and distribution list

| Project Role | Name | E-mail | Date |
| --- | --- | --- | --- |
| Instructor | Anjana Shah | ashah@georgebrown.ca | October 7, 2024 |
| Project Manager | Jacob Solano | 101348583@georgebrown.ca | October 7, 2024 |
| Lead Frontend Developer | Nhu Nam Nguyen | 101441905@georgebrown.ca | October 7, 2024 |
| Lead Backend Developer | Duc Thien Tran | 101333237@georebrown.ca | October 7, 2024 |
| Full Stack Developer | Ronan Behan | 101366894@georgebrown.ca | October 7, 2024 |
| Full Stack Developer | Simon Vu | 101415605@georgebrown.ca | October 7, 2024 |

3. Scope

Define the sum total of all of its products and their requirements or features.

| In Scope | Out of Scope |
| --- | --- |
| User registration and profile creation | Integration with fitness tracking devices or other third-party apps |
| Geolocation services for nearby partner and gym suggestions | Implementation of a payment system for premium features |
| Filter-based and swipe-based matching system | Development of a web-based version of the application |
| In-app messaging and communication | Social media integration |
| Workout tracking and challenges | Creation of content such as workout plans or nutritional advice |
| User verification and reporting system |  |
| Integration with Google Maps for gym locations |  |
| Backend infrastructure and database management |  |
| iOS and Android mobile application development |  |

4. Deliverables

This project will deliver the following.

| Deliverable | Description |
| --- | --- |
| Mobile Application | Fully functional GymBuddies app for iOS and Android platforms |
| Backend Infrastructure | Server infrastructure to support user data management, matching algorithm, and API services |
| Documentation | Comprehensive documentation including user manuals, API documentation, and system architecture diagrams |
| Final Presentation | Presentation and demo of the application, showcasing key features and potential for scalability |

5. Assumptions

This project makes the following assumptions:

- Resources will be available to host the application

- The app will be created using Android Studio with the latest SDK for Android and Swift for iOS

- All planned features of the app can be implemented within the project timeframe

- The project will be able to attain its current scope

- The application will allow seamless integration of users

- Google Maps will be used for integrating location services

- The app will comply with PIPEDA privacy regulations

6. Dependencies

The following are the internal and external dependencies that will have to be acknowledged and addressed:

- Availability of Google Maps API for location services

- Access to cloud services (Firebase) for backend infrastructure

- Approval and compliance with app store guidelines (Google Play Store and Apple App Store)

- Collaboration with ad agencies for in-app advertisement integration

7. Risk Management

| Potential Risk | Severity (H/M/L) | Likelihood (H/M/L) | Management Strategy |
| --- | --- | --- | --- |
| User safety concerns | H | M | Implement robust verification and reporting systems. Provide safety guidelines |
| Privacy regulation non-compliance | H | L | Regularly review and update privacy policies |
| Low initial user adoption | H | H | Develop a strong marketing strategy Offer incentives for early adopters |
| Technical issues/bugs | M | M | Implement thorough testing procedures Establish a quick response system for bug fixes |
| Scalability challenges | M | L | Design the backend infrastructure for scalability from the start |

8. Communication

Reporting

The following reports will be produced:

| Report | Audience | Frequency |
| --- | --- | --- |
| Progress Report | Team Members, Anjana Shah | Weekly (During Class) |
| Sprint Review | Team Members, Anjana Shah | End of each Sprint |

Meetings

The following meetings/communication will be established;

| Meeting | Purpose | Attendees | Frequency |
| --- | --- | --- | --- |
| Minutes of Meeting | Plan Sprint Deliverables | Team Members | Every 3 days |

9. Task Listing (WBS- Work Breakdown Structure)

| Reference | Tasks | Duration | Dependency |
| --- | --- | --- | --- |
| A | Sprint 1 | 2 Weeks | - |
| A.1 | Project Vision |  | A |
| A.2 | Business Requirements |  | A.1 |
| A.3 | Personas |  | A.2 |
| A.4 | User Stories |  | A.3 |
| B | Sprint 2 | 3 Weeks | A |
| B.1 | Project Plan |  | A |
| B.2 | Team Charter |  | B.1 |
| B.3 | Product Backlog |  | B.2 |
| B.4 | Sprint Backlog |  | B.3 |
| B.5 | Preparation and Class Presentation |  | A, B |
| C | Sprint 3 | 3 Weeks | B |
| C.1 | System Requirements Gathering |  | C |
| C.2 | Analysis and Design |  | C.1 |
| D | Sprint 4 | 4 Weeks | C |
| D.1 | Wireframes/Prototype |  | C |
| D.2 | Technical Requirements |  | D.1 |
| E | Backend Development | 3 Weeks | D |
| E.1 | Set up cloud infrastructure (Firebase) |  | D |
| E.2 | Develop user authentication system |  | E.1 |
| E.3 | Create API for user profile management |  | E.2 |
| E.4 | Implement matching system |  | E.3 |
| E.5 | Implement API for geolocation services |  | E.4 |
| E.6 | Implement ad serving API |  | E.5 |
| F | Frontend Development (iOS) | 4 Weeks | D |
| F.1 | Implement user registration and login |  | D |
| F.2 | Create user profile management interface |  | F.1 |
| F.3 | Develop match finding and filtering interface |  | F.2 |
| F.4 | Implement in-app messaging system |  | F.3 |
| F.5 | Create workout tracking and challenge features |  | F.4 |
| F.6 | Implement user verification system |  | F.5 |
| F.7 | Integrate geolocation services |  | F.6, E.5 |
| F.8 | Implement ad display system |  | F.7 |
| G | Frontend Development (Android) | 4 Weeks | D |
| G.1 | Implement user registration and login |  | D |
| G.2 | Create user profile management interface |  | G.1 |
| G.3 | Develop match finding and filtering interface |  | G.2 |
| G.4 | Implement in-app messaging system |  | G.3 |
| G.5 | Create workout tracking and challenge features |  | G.4 |
| G.6 | Implement user verification system |  | G.5 |
| G.7 | Integrate geolocation services |  | G.6, E.5 |
| G.8 | Implement ad display system |  | G.7 |
| H | Integration and Testing | 4 Weeks | E, F, G |
| H.1 | Integrate backend with iOS frontend |  | E, F |
| H.2 | Integrate backend with Android frontend |  | E, G |
| H.3 | Develop reporting and safety features |  | H.2 |
| H.4 | Test and optimize ad system |  | H.3 |
| I | Quality Assurance and Bug Fixing | 2 Weeks | H |
| I.1 | Conduct thorough testing of all features |  | H |
| I.2 | Fix identified bugs and issues |  | H.1 |
| J | Documentation and Finalization | 1 Week | I |
| J.1 | Create user manuals |  | I |
| J.2 | Prepare API documentation |  | I |
| J.3 | Finalize system architecture diagrams |  | I |
| K | App Store Submission | 1 Day | J |
| K.1 | Prepare submission for iOS App Store |  | J |
| K.2 | Prepare submission for Google Play Store |  | J |

10. Budget

- The project would utilize the free version of the Firebase and the free version of the Google Maps API to implement the features of the app during its developmental cycle.

- Google Maps API provides $200 worth of free credits every month. The first 100,000 requests would cost $32 per 1000 requests. This leads to 6,250 worth of free requests a month.

- The quota for free Firebase users consist of:

  - Stored data - 1 GiB

  - Document reads - 50,000 per day

  - Document writes - 20,000 per day

  - Document deletes - 20,000 per day

  - Outbound data transfer - 10 GiB per month

- The team members would utilize caching strategies to limit API calls and optimize database and queries to take advantage of the free tiers provided by Firebase and Google Maps API

11. Milestones

| Major Activity or Milestone | Estimated Milestone Target date | Owner/Reviewer Team Members |
| --- | --- | --- |
| Project Kickoff | September 16, 2024 | Team Members |
| Sprint 1 Completion | September 29, 2024 | Team Members |
| Sprint 2 Completion | October 7, 2024 | Team Members |
| Sprint 3 Completion | November 18, 2024 | Team Members |
| Sprint 4 Completion | December 20, 2024 | Team Members |
| Backend MVP | Januray 21, 2025 | Duc Thien Tran, Nhu Nam Nguyen |
| Frontend MVP (iOS and Android) | January 28, 2025 | Ronan Behan, Simon Vu |
| Integration Complete | Februrary 25, 2025 | Team Members |
| Debugging Complete | March 11, 2025 | Team Members |
| Documentation Complete | March 18, 2025 | Team Members |
| App Store Submission | March 20, 2025 | Jacob Solano |
| Project Completion | March 28, 2025 | Team Members |

12. Approval

The signatures below indicate their approval of the contents of this document.

| Project Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager | Jacob Solano | Jacob Solano | October 7, 2024 |
| Lead Frontend Developer | Nhu Nam Nguyen | Nhu Nam Nguyen | October 7, 2024 |
| Lead Backend Developer | Duc Thien Tran | Thien Tran | October 7, 2024 |
| Full Stack Developer | Ronan Behan | Ronan Behan | October 7, 2024 |
| Full Stack Developer | Simon Vu | Simon Vu | October 7, 2024 |